Suggested 2018-19 DCSS MS-HS Student Science Fair Timeline

| ### Critical Dates | ### Item/Event Description |
| --- | --- |
| August 23 | Deadline for students to return SIGNED parent permission letters |
| August 27 | Deadline for logbook purchase. |
| September 11 | Topic Deadline/Topic Approval. Checkpoint #1 Worksheet Due Note: If your plans involve human subjects (even if it’s just to ask them questions for a survey), animals or animal tissue, micro-organisms, DNA, radiation, controlled or hazardous substances, explosives, or chemicals not generally found in a household, you your project has to be approved by the SRC/IRB before you start your project. |
| September 19 | Last day for students to begin background research. |
| September 21 | Last day to submit Project Proposal to your teacher for her to approve or if teacher cannot approve she/he will submit the proposal to SRC/IRB for approval or rejection of project. STUDENTS that have projects submitted to the SRC/IRB cannot begin their experimentation until they get the approval form back from the SRC/IRB. |
| September 28 | Deadline for 3 required GSEF forms needed at region fair (checklist for adult sponsor, research plan 1A, approval plan 1B) http://student.societyforscience.org/forms |
| October 1 | Checkpoint #2 Worksheet Due |
| October 3 | Final day for the development of the anticipated research experiment plan (teacher oks) |
| October 15 | Final day for students to begin experiment |
| October 26 | Rough Draft Due (including cover-page, partial abstract (excluding results), table of contents, introduction, background information, hypothesis, procedures, and materials. Students should exclude results from experiment, as they may still be experimenting) Abstract form at http://student.societyforscience.org/forms |
| November 15 | All Science Fair experimentation should be done |
| Set by teacher | During this time: Tri-Panel Display, logbook and formal report due to teachers; projects should be presented to the class, and graded as well. |
| Dec. 3 to January 4 | Individual School Science Fairs |
| Jan. 7th , 2019 | Turn in student entries to Central office by Noon today. Email to pamela.walker@dcssga.org |
| January 14, 2019 | Projects may be set up at the annex (Murray Center) from 3:00-5:30 this afternoon |
| January 15, 2019 | Set-up, judging and interviews at the Annex (unless otherwise noted). All set up should be completed by 10:00AM this morning. Judging begins at 1:00. Student interviews begin at 4:00PM |
| January 17, 2019 | Douglas County School System Science Fair Award Ceremony and Project Removal Project viewing for public 5:15-6:15; Awards ceremony begins at 6:30PM |
| TBA (early Feb. 2018) | University of West Georgia Regional Science Fair |